## About
DSUR responsibility (RACI) matrix
Companion material to Writing the DSUR (Selim Medical Press). Fictional data. Not regulatory advice. CC BY-NC 4.0.
What it is: the responsibility matrix for a DSUR from Writing the DSUR, Chapter 3 (3.3, Figure 3.2) and Appendix C.3, as an editable sheet.
How to use it: settle it at the kickoff meeting. Edit the codes on the RACI sheet (drop-down: A, R, C, I, A/R). Keep exactly one accountable person per row.
Related: the timeline back-planner (tools/timeline-back-planner.html) and the year-round records workbook (ch03-year-round-records.xlsx).

## RACI
DSUR section | Safety physician | Safety scientist | Clinical development | Biostatistics | Regulatory | Medical writer | Vendor (CRO) | Partner | Accountable entries in row
Scope record, Sections 1–2 | A | C | C | I | R | R
3 Actions taken | A | R | C | I | C | R
4 Changes to RSI | A | R | C | I | I | R
5–6 Trial inventory, exposure | I | C | A | R | I | R
7 Listings and tabulations | C | A | I | R | I | C
8 Trial findings | C | C | A | R | I | R
9–15 Other sources | A | R | C | I | C | R
16 Region-specific | I | C | C | I | A | R
17 Late-breaking | A | R | C | I | I | R
18–19 Assessment, important risks | A/R | R | C | C | I | R
20 and Executive Summary | A | C | C | I | C | R
QC and submission | I | C | I | C | A | R
A = accountable, R = responsible, C = consulted, I = informed.
This is the proposed model from Chapter 3 (Figure 3.2) and Appendix C.3; adapt it to your organization, but keep one accountable person per row. Column J counts the accountable entries in each row and turns red when the count is not 1.
When a vendor or partner is involved, use the Vendor (CRO) and Partner columns (add more if needed). A contract research organization that drafts sections becomes R for those sections; the sponsor keeps A for every row, because the sponsor remains responsible for the report's content (E2F §2.4.1). A partner that supplies data is R for delivering them on the agreed day and C for the sections that use them.
Two features of the model are deliberate: the safety physician is both accountable and responsible for Sections 18 and 19, and clinical development is accountable for the trial inventory and trial findings (Chapter 3, 3.3).