## About
DSUR QC log (Chapter 15)
Companion material to Writing the DSUR (Selim Medical Press). Fictional data. Not regulatory advice. CC BY-NC 4.0.
What it is for:
Record every QC finding with its level, location, the reviewer, the date, the resolution, the person who resolved it and the date of the fix. Record checks that found nothing too: "Section 7.1 RSI checked against listings: consistent" is evidence that the check was done (Writing the DSUR, 15.5). The log goes in the DSUR file (15.6) and is the single most useful document in an inspection.
How to use it:
QC log sheet: one row per finding, check or note. Entry type, Layer, Level and Status are fixed lists; dates are validated. "Must be fixed before" fills in from the level (Levels sheet, from 15.5).
Layer: Traceability = every number traces to a table or listing and every table to a dated source extract; Logic = every conclusion traces to evidence shown in the report (15.2).
Use the key-figures tracker (ch13) for traceability QC, and the interactive QC checklist (tools/qc-checklist.html, Appendix B) for the high-yield checks.
Example (Case B) sheet: entries from XB-7's QC, built from 15.4 (draft 2 QC on 8 October 2026) and the Chapter 15 opening scenario (24 September 2026). Reviewers are shown by role.
At the end of each cycle, review the log: if the same kind of error appears every year, fix it upstream, in the data request, the TFL specification or the template.
Owner: the medical writer keeps the log (Chapter 15 role notes).

## QC log
No. | Draft or version | Entry type | Layer | Location | Finding or check | Level | Must be fixed before | Reviewer | Date found | Resolution | Resolved by | Date resolved | Status

## Example (Case B)
No. | Draft or version | Entry type | Layer | Location | Finding or check | Level | Must be fixed before | Reviewer | Date found | Resolution | Resolved by | Date resolved | Status
1 | Draft 1 output | Finding | Traceability | Regional cumulative tabulation | Expectedness in the draft tabulation was assessed against the current IB, Edition 6, so both sepsis cases appeared as expected. The RSI for this DSUR is Edition 5, in effect at the start of the period (Section 7.1). | Critical |  | Safety scientist | 2026-09-24 | Tabulation rerun against IB Edition 5; regenerated output saved with its run date and program version; final table approved. Both sepsis cases now shown as unexpected, matching how they were expedited. | Biostatistician | 2026-09-24 | Closed
2 | Draft 2 | Finding | Traceability | Section 19 | Interval exposure given as about 410 subject-years; the source (exposure dataset, run 3 Sep 2026) and Sections 6 and 18.1 give about 400. Section 19 was drafted from a preliminary extract run before the last XB-302 visits were entered. | Major |  | Traceability reviewer | 2026-10-08 | Section 19 corrected to about 400 subject-years. The rate was already calculated from the final extract and did not change. | Medical writer | 2026-10-08 | Closed
3 | Draft 2 | Finding | Traceability | Executive Summary | Cumulative serious infections given as 30; the cumulative SAE tabulation and Sections 18.1 and 19 give 31. The summary was drafted before a late serious infection was reconciled into the tabulation. | Major |  | Traceability reviewer | 2026-10-08 | Executive Summary corrected to 31. | Medical writer | 2026-10-08 | Closed
4 | Draft 2 | Check (no finding) | Traceability | Section 7.1; listings; tabulation | Section 7.1 RSI checked against listings and tabulation: consistent (IB Edition 5). Serious infections in the period checked across Executive Summary, Sections 18.1 and 19 and tabulation: consistent (14). |  |  | Traceability reviewer | 2026-10-08 | None needed. |  |  | Closed
5 | Draft 2 | Finding | Logic | Section 20 | Section 20 says "No changes to the development program are required." Section 18.1 describes the DMC's post-DLP recommendation of infection assessment at each visit for subjects over 75 or on corticosteroids, accepted by the sponsor. A reader cannot tell which is true. | Critical |  | Logic reviewer (safety physician, another program) | 2026-10-08 | Section 20 rewritten: "The sponsor has accepted the DMC's recommendation to add infection assessment at each visit for subjects over 75 years or receiving corticosteroids; a protocol amendment is in preparation (Sections 17 and 18.1). No other changes to the development program are required." | Safety physician (DSUR lead) | 2026-10-09 | Closed
6 | Draft 2 | Note | Logic | Section 18.1 | Question: Section 18.1 says the rate of 3.5 is modestly above the 2.7 expected. Would the conclusion change if the true exposure were 10 percent lower? |  |  | Logic reviewer (safety physician, another program) | 2026-10-08 | Biostatistician checked: the rate would be about 3.9, and the conclusion (difference small and partly explained by the older population of XB-302) still holds. No change; recorded so the reasoning is on file. | Biostatistician | 2026-10-08 | Closed

## Levels
Level | Definition | Example | Must be fixed before
Critical | Changes a conclusion, or misstates a regulator-facing fact | Wrong RSI; Section 20 contradicts Section 18 | Next review round
Major | A factual error that does not change a conclusion | Wrong exposure in one section; totals that disagree | Final QC
Minor | Style, formatting or presentation | Inconsistent decimal places; a broken cross-reference | Publishing